# SECTION 513 – MOBILIZATION

## 513.01 – Description

This work shall consist of performing preliminary operations, including: moving personnel and equipment to the project site; paying bonds and insurance premiums; and establishing the Contractor’s offices, buildings, and other facilities necessary to allow work to begin on a substantial phase of the Contract.

## 513.02 – Measurement and Payment

Mobilization will be paid for at the Contract lump sum price. This price shall include demobilization.

Payment for mobilization up to the limitations specified herein will be made in two separate installments. The first installment of 50 percent of the Contract lump sum price for mobilization will be made on the first progress estimate following partial mobilization and initiation of construction work. The second installment will be made on the next progress estimate following completion of substantial mobilization, including erection of the Contractor’s offices and buildings. Completion of erection of processing plants, if any, will not be required as a condition for the release of the second installment.

If the original Contract lump sum price for mobilization exceeds the total mobilization payout limit stated in the table below, the excess will be included on the semifinal estimate.

| Contract Amount |  | Total Mobilization Payout Limit |
| --- | --- | --- |
| More Than | To and Including |  |
| $0 | $200,000 | 10% of total contract amount |
| 200,000 | 1,000,000 | $20,000 plus 7.5% (of total contract amount minus $200,000) |
| 1,000,000 | More | $80,000 plus 5% (of total contract amount minus $1,000,000) |

No additional payment will be made for demobilization and remobilization because of shutdowns, suspensions of work, or other mobilization activities.

When not shown as a pay item, the cost of mobilization shall be included in the price bid for other appropriate items of work.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| Mobilization | Lump sum |