GUIDELINES — For Renewable On Call projects only.

SP100-000120-01

VIRGINIA DEPARTMENT OF TRANSPORTATION

SPECIAL PROVISION FOR

RENEWABLE ON CALL CONTRACTS GENERAL PROVISIONS

November 4, 2020

SECTION 101 – DEFINITIONS OF ABBREVIATIONS, ACRONYMS, AND TERMS of the Specifications is amended as follows:

Section 101.02 – Terms is amended to include the following:

Renewable Contract. A contract that may be extended for additional terms.

Task Order. An assignment of specific work, work schedule, or plan details depicting work to be performed at a location or locations defined by physical description. Each Task Order will be issued with a Notice to Proceed specifying the Task Order value, required work commencement date, the Liquidated Damages, and the completion date/days of the Task Order. The Task Order will include a description of the work to be performed with plan details or schedules, estimated quantities and site specific limitations of operations.

Task Order Completion Date. The date, specified in an issued Task Order, by which the Contractor shall achieve Final Acceptance by the Department on the work described in the Task Order in accordance with Section 108.09. This date may be modified by two-party signing of the revised Task Order.

Term. The time limit and conditions of the Contract in force from the Contract Execution Date until the first of either the original Completion Date, including any authorized extensions thereto, or the date on which the cumulative payments for completed and accepted work reaches the original Contract amount.

SECTION 103 – AWARD AND EXECUTION OF CONTRACTS of the Specifications is amended as follows:

Section 103.02 – Award of Contract is renamed Award of Contract and Contract Renewal and amended to include the following:

The Department may extend the Contract in order for the Contractor to complete scheduled work or work underway. In addition, the Department may renew the Contract after the completion of the original Term for two additional Terms of one year each, provided the Department and Contractor are in agreement and the following conditions are met:

1.	The Contractor’s bonding agency provides written proof that it is in agreement with the Contract Renewal.

2.	There are no increases in unit prices or to unit prices added to the original contract by any authorized Change Order thereto as a condition of the renewal.

3.	No new work items are added as a condition of the renewal beyond those authorized in accordance with item 2. herein.

4.	The Contractor provides proof of insurance for the Contract Renewal Term in accordance with Section 103.06.

Section 103.05(a) – REQUIREMENTS OF CONTRACT BOND is replaced with the following:

A performance bond, valued at the lesser of the Contract Value or $fill-in, conditioned upon the faithful performance of the Contract in strict conformity with the Plans, the Specifications and conditions of the Contract.

Section 103.05(b) – REQUIREMENTS OF CONTRACT BOND is replaced by the following:

A payment bond, valued at the lesser of the Contract Value or $fill-in, conditioned upon the prompt payment for all labor, materials, public utility services and rental of equipment used in the prosecution of the work for the Contract.

SECTION 104 – SCOPE OF WORK of the Specifications is amended as follows:

Section 104.01 – Intent of Contract is amended to replace the first sentence with the following:

The intent of this Contract is to provide for furnishing sufficient labor and equipment, delivering goods and services, and maintaining adequate material on hand to respond to the Department's need for timely completion of the Work assigned by Task Order in one or more of the Department's Construction Districts. This Contract shall be in accordance with Task Order plans and sketches and the Specifications and provisions herein. The estimated bid quantities are based on existing conditions or quantities historically used in the geographic area of the Contract. Renewable On Call contracts will serve as a cost effective and timely response contracting method when the Department anticipates the need for a variety of goods or services for specific purposes; however, the actual demand is not known and delivery of the goods or services is made when a requirement arises. Work on this Contract is to be performed, completed, and accepted within Task Order time limits and within the Term of the Contract. During the Term of the Contract, the Department will issue Task Orders to the Contractor with a cumulative value that will equal or exceed 70% of the original value of the Contract, unless the Contract is terminated according to Section 108.08 of the Specifications.

Section 104.02 – Alteration of Quantities or Character of Work is amended to include the following:

Quantity changes in an On Call Contract shall not be construed as a significant change.

Budgetary constraints may be imposed by the Department at any time during the life of the Contract. The Contractor will be notified if the Engineer determines that the cost of completing the Work will exceed available funding or budget as may be adjusted by the Department. Task Orders with work underway shall be completed or the work shall be suspended and the work site restored as directed by the Engineer. The Engineer will specify which previously issued Task Orders will be rescinded according to the Department’s predetermined priorities.

If further analysis indicates that the cost of work underway will fall below the limits of the budgeted funds, the Engineer may issue additional Task Orders to be completed by the Contractor at contract unit prices.

SECTION 105 – CONTROL OF WORK of the Specifications is amended as follows:

Section 105.01 – Notice to Proceed is amended to include the following:

Task Orders will be issued to the Contractor specifying the location, value, time limit, liquidated damages, and description of work or design plans of work to be performed. During the project, the Engineer will coordinate with the Contractor on anticipated Task Orders to assist inventory control.

Section 105.03(a) – Authority of the Engineer is amended to include the following:

The Engineer may extend the contract time limit or renew the contract in accordance with Section 103.02 herein.

SECTION 107 – LEGAL RESPONSIBILITIES of the Specifications is amended as follows:

Section 107.02 – Permits, Certifications, and Operations is amended to include the following:

All contract work shall conform to permit conditions and regulatory approvals as detailed in the proposal or provided to the Contractor with a Task Order.

SECTION 108 – PROSECUTION AND PROGRESS OF WORK of the Specifications is amended as follows:

Section 108.01 – Prosecution of Work of the Specifications is amended to include the following:

The Contractor shall be prepared to begin work on a Task Order on the date specified in the Notice to Proceed, unless otherwise approved by the Engineer.

If the Contractor opts to suspend work temporarily on a Task Order or portion thereof, the Contractor shall notify the Engineer at least 24 hours in advance of the time and date he plans to pull off the work site. The Contractor shall ensure the work site has been properly and safely secured to protect the traveling public in accordance with the VWAPM, the MUTCD, or specific language in the Contract before leaving the work site. Temporary suspension of the work does not relieve the Contractor of the obligation to complete the Task Order on or before the date specified in the Notice to Proceed nor will it delay Liquidated Damages assessment.

Section 108.02(a) – General is  replaced with the following:

General

Contract work not detailed in the proposal shall not proceed until the Engineer issues the Contractor a written Task Order releasing the work. No work requiring shop drawings, catalog cuts, pre-approval items, or materials certifications will be released until all applicable items have been reviewed by the Engineer.

The Contractor shall conduct the work in a manner and sequence that will ensure its expeditious completion with the least interference to traffic and shall have due regard for the location of detours and provisions for handling traffic. The Contractor shall not open any work to the prejudice or detriment of work already started. The Engineer may require the Contractor to finish a Task Order or portion thereof before work is started on any other Task Order or portion thereof.

Limitations specific to individual Task Order locations will be provided to the Contractor with the Task Order Notice to Proceed.

Section 108.03(b) – Progress Schedule Submission Requirements is amended by replacing the first paragraph and bulleted paragraphs with the following:

The Contractor shall submit to the Engineer three copies of the written Schedule of Operations at least 7 Days before beginning work on each Task Order. The Schedule of Operations shall represent the Contractor’s overall work plan to accomplish the Task Order in accordance with the Contract. The Progress Schedule shall include all work including, as applicable, the work to be performed by sub-contractors, the Department, or others. The Progress Schedule submittal shall consist of a written Narrative to:

- Describe the Contractor’s proposed general sequence to accomplish the work.

- Indicate the general schedule of work to be completed each week in terms of major operations, routes, or segments of work for each Task Order released by the Department or in the absence of such delineation, as agreed to by the Contractor and the Engineer. A bar-chart schedule may be substituted at the Contractor’s option.

Section 108.03(b)1 – Two Week Look-ahead (TWLA) Progress Schedule is replaced by the following:

At least 7 Days before beginning work, the Contractor shall submit to the Engineer, an initial written TWLA Progress Schedule for any work planned for the first two weeks. Every week thereafter, on a day agreed to by the Contractor and the Engineer, the Contractor shall submit to the Engineer, a written TWLA Progress Schedule for the following two-week period. The TWLA schedule shall provide a detailed list of operations to indicate the type of operation, locations of the work, proposed working days and hours, and the start and finish dates for any work planned, started, in progress, or scheduled for completion during the two-week period. The TWLA Progress Schedule shall also indicate any critical stages of work requiring Department oversight or inspection.

The TWLA shall indicate all current Task Orders, their start dates, and anticipated construction completion dates. In addition, if applicable, the TWLA shall include any outstanding issues associated with each Task Order that may, for example, affect or impact operations schedule, completion dates, equipment, other stakeholders, etc. The Contractor shall submit three copies of the TWLA to the Engineer via email with copies to other stakeholders as mutually agreed upon.

Section 108.06(b) – Liquidated Damages is amended by replacing the first paragraph with the following:

Liquidated Damages, representing the cost of administration, engineering, supervision, inspection, and other expenses will be charged against the Contractor for each Day beyond the fixed time/days that a Task Order remains in an incomplete state. A daily Liquidated Damage amount will be calculated for each Task Order in accordance with Table I-1. Liquidated Damages will be assessed concurrently for each individual Task Order. If multiple Task Orders remain incomplete, Liquidated Damages will be assessed on all incomplete Task Orders concurrently.

Table I-1 – Schedule of Liquidated Damages is replaced with the following:

| TABLE I-1 Schedule of Liquidated Damages |  |
| --- | --- |
| Task Order Value in Dollars | Daily Charge in Dollars |
| 0.00 - 500,000.00 | 350 |
| 500,000.01 - 2,000,000.00 | 600 |
| 2,000,000.01 - 8,000,000.00 | 1,350 |
| 8,000,000.01 - 15,000,000.00 | 2,500 |
| 15,000,000.01 or more | 3,100 |

Section 108.07 – Default of Contract is amended to replace condition (a) with the following:

fails to begin the work assigned by a Task Order within 15 Days after that Task Order’s Notice to Proceed, except as otherwise permitted by specific contract language or the provisions of Section 105.01 or Section 108.02 of the Specifications or if the Contractor does not complete a Task Order by the Task Order Completion Date.

SECTION 109 – MEASUREMENT AND PAYMENT of the Specifications is amended as follows:

Section 109.05(a) – Payment for Extra Work is amended to include the following:

If the Engineer determines that this Contract should be renewed for another term and the Contractor agrees to the renewal, a bilateral Work Order will be executed to authorize the work for an additional term.

Section 109.09 – Payment for Material on Hand of the Specifications is replaced with the following:

No payment for material on hand will be made for this contract.

SECTION 510 – RELOCATING OR MODIFYING EXISTING MISCELLANEOUS ITEMS of the Specifications is amended as follows:

Section 510.03 – Procedures is amended to include the following:

When the contract specifies an "Install" item, the Contractor shall furnish all other materials necessary to complete the installation. All materials required to complete the installation and not covered by a separate contract item shall be considered incidental to installation and shall be included in the contract unit price for the "Install" item.

Equipment or materials furnished by VDOT to be installed by the Contractor shall be picked up by the Contractor at a VDOT facility designated by the Engineer between the hours of 8:00 a.m. and 3:30 p.m. Monday through Friday. The Contractor shall notify the Department at least 24 hours before picking up equipment or materials.

Equipment or material to be returned to VDOT by the Contractor shall be delivered to a VDOT facility designated by the Engineer between the hours of 8:00 a.m. and 3:30 p.m. Monday through Friday. The Contractor shall notify the Department at least 24 hours before delivering equipment.

Equipment supplied by a municipality to be installed by the Contractor shall be picked up at a facility within the municipality.

SECTION 512 – MAINTAINING TRAFFIC of the Specifications is amended as follows:

Section 512.03 – Procedures is amended to include the following:

The Contractor shall submit a Maintenance of Traffic Plan with quantities for each Task Order work zone and any planned lane or shoulder closures for review by the Engineer, before commencement of work. The maintenance of traffic plan shall be in accordance with the VWAPM and the MUTCD.

If conditions dictate, the Engineer may incorporate the use of law enforcement personnel within the work zone.

Section 512.04 – Measurement and Payment is amended to replace Temporary (Construction) Signs with the following:

The Contractor shall furnish, install, maintain, relocate, cover, uncover, and remove all temporary construction sign panels, sign supports, hardware, delineators, and flags. The cost thereof shall be included in the price bid for other appropriate items. All signs shall be in accordance with Section 512, VWAPM, and MUTCD.

SECTION 513 – MOBILIZATION of the Specifications is amended as follows:

Section 513 .01 Description is replaced with the following:

On Call  Mobilization shall consist of performing preparatory operations, including moving personnel and equipment to a site or sites within an Area defined by jurisdictional boundaries or in the Contract, when work is issued in a Task Order under this Contract. Task Orders will be issued as necessary within one or multiple Areas. When a pay item, mobilization will be paid based on the Area and value of the Task Order in each respective Area.

It is anticipated that any Task Order issued for this Contract will be greater than:

$ (fill-in)

Section 513.02 Measurement and Payment is replaced with the following:

Mobilization on-call task order will be measured in units of each, based on the Area and value of the Task Order, to mobilize to one or more sites to perform all work identified in each respective task order and will be paid at the Contract each price. Mobilization will be paid once per task order, per Area as issued by the Engineer. The price shall include moving personnel, materials and equipment to the project sites per Area per task order and demobilization when no longer required. The price also includes, but is not limited to, as many return trips as necessary due to holidays, curing time or temperature requirements, and manufacturer recommendations.

No additional payment will be made for demobilization and remobilization because of shutdowns, suspensions of work, or other mobilization activities. Mobilization to a structure with one end in each of two Areas will be paid only once at the higher rate of the two areas.

Payment for mobilization will be made on the basis of two installments per task order.  The first installment will be made at 50% of the contract unit price per each and will be made on the next progress estimate after mobilization. Payment of the remaining 50% will be made on the progress estimate following completion and acceptance of the work and demobilization.

When not a pay item the cost of mobilization shall be included in the price of other appropriate items of work.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| Mobilization On-Call Task Order Greater than $Amount (Area) | Each |
| Mobilization On-Call Task Order Less than $Amount (Area) | Each |