Guidelines: Design-Build Projects with bridgework involving erection of structural steel members.

SP407-DB0500-00

VIRGINIA DEPARTMENT OF TRANSPORTATION

SPECIAL PROVISION FOR

SUPERSTRUCTURE ERECTION STABILITY

June 10, 2022

- DESCRIPTION

This work shall consist of preparing and submitting primary member erection plans and procedures meeting the superstructure erection stability requirements herein to the Design Manager and the Department for review. The Design-Builder remains solely responsible: for the means and methods to be used to stabilize and maintain all structural members during all stages of construction, including but not limited to, transporting, storing, lifting, placing, and post-erection; and for any errors, omissions, or risks inherent in the Erection Plans and Procedures, and in the supporting documentation. The Design Manager and Department’s review of the Design-Builder’s submittal for primary member erection plans and procedures will be limited to conformance with the Contract requirements.

The Design-Builder shall perform and prepare all erection engineering calculations, drawings, and documentation required to successfully erect the superstructure. Erection engineering calculations, drawings, and documentation shall be submitted in accordance with the Stability Classifications established herein, or as requested by the Design Manager.

This Special Provision supplements Sections 405 and 407 of the Specifications.

- DEFINITIONS

  - Active Work Space – An area, or portion thereof, where construction or erection activities are actively in progress or personnel are present.

  - Erection – The process including handling, shipping and assembling the bridge structural steel, prestressed concrete, or post-tensioned concrete superstructure.

  - Erection Engineer – A Professional Engineer retained by the Design-Builder to provide professional engineering services and complete calculations required herein. An Erection Engineer shall be a Professional Engineer licensed to practice engineering in the Commonwealth of Virginia.

  - Erection Engineering Calculations – Engineering calculations associated with the development and substantiation of the Erection Procedures.

  - Erection Plans and Procedures – The engineering drawings, calculations, and specifications prepared by the Erection Engineer describing the erection (e.g., the field-installation, member-placement, and temporary support) of the primary members, the specific sequence, methods, equipment, and other procedures that the Design-Builder plans to use in erecting the primary  members.

  - Erection Supervisor – The person responsible for all rigging and handling of bridge members. The Erection Supervisor shall be present at the erection site during the erection of primary members.

  - Erector – The firm responsible for the erection of the primary members; may be self-performed by the Design-Builder or a subcontractor specializing in the erection of primary members.

  - Inactive Work Space – An area, or portion thereof, where construction or erection activities have ceased for a period of time and personnel are not present (e.g., area vacated at the end of a work shift, overnight, or during inclement weather).

  - Primary Member – A steel or concrete member designed to carry the loads applied to the structure as determined from an analysis. May include a superstructure beam, girder, truss, cross-frames or diaphragms.

  - Shoring Tower – A structure that is used to temporarily support superstructure segments prior to those segments being made into a continuous girder.

  - Strongback – A beam or girder that acts as a secondary support member to superstructure elements. The superstructure elements may not be safe during construction without the strongbacks.

  - Temporary Support Structure – A temporary structure that is required during shipping or erection to support or stabilize the structure, or a portion of the structure, and is removed when no longer required for structural support or stabilization.  Temporary support structures may include but are not limited to strongbacks, falsework, hold cranes, tie-downs, and primary member restraints.

  - Superstructure Unit - Composed of all spans in a continuous portion of superstructure. Units may be continuous for live load only (e.g., prestressed concrete beams) or dead load and live load (e.g., structural steel plate girders).

- BRIDGE STABILITY CLASSIFICATIONS

Bridge superstructure units will be classified as Stability Class SA, SB, or SC according to the following conditions:

Table III-1: Summary of Geometric Requirements

| DESCRIPTION |  | Class SA | Class SB | Class SC |
| --- | --- | --- | --- | --- |
| LONGEST SPAN LENGTH | CONCRETE | 0’ to 75’ | > 75’ to 135’ | > 135’ |
|  | STEEL | 0’ to 100’ | > 100’ to 160’ | > 160’ |
| CURVED GIRDER | CONCRETE | N/A |  |  |
|  | STEEL | N/A | L/R < 0.05 | L/R > 0.05 |

L = span length, bearing to bearing along the centerline (CL) of the member of the controlling span.

R = the radius of the centerline of the member.

If a bridge superstructure unit meets multiple classes, use the highest class. Class SA is lower than Class B, and Class B is lower than Class SC.

For a bridge over in-service roadways or railroads and its longest span length meets Class SA, use Class SB as the minimum stability class.

If shoring tower, strongback or falsework is required, use Class SC.

If a bridge superstructure unit is not covered in this table, the Engineer will specify the stability classification.

- MEETINGS AND SUBMITTALS

  - The Erection Plans and Procedures shall describe and specify all aspects of how the structural members are to be erected, including, but not limited to, transportation and shipping, sequence of erection, methods or techniques to be used, equipment to be used, and materials to be used, along with any temporary works or other devices necessary.

  - The Erection Plans and Procedures shall be signed and sealed by the Erection Engineer.  For Class SC, the Erection Plan and Procedures for each primary member shall be reviewed by the Fabricator prior to submittal to the Design Manager for potential issues related to constructability, fabrication feasibility, and ease of shipping.  The Fabricator shall provide the Design-Builder a summary of findings; the Design-Builder shall include the Fabricator’s review summary, with Design-Builder’s disposition for each comment provided, with the Erection Plans and Procedures submittal to the Design Manager and the Department for review.

  - The Erection Plans and Procedures shall include, but not be limited to, the following:

      - Handling and Shipping Plan – A handling and shipping plan shall be included for all Stability Classes SB and SC members with shipping lengths greater than 75 feet. This plan shall include the following:

        - Shipping length and weight.

        - Truck/rail/barge & load configuration sketches.

        - Tie-down configurations and tightening process.

        - Anticipated hauling routes.

        - Method of shipping (e.g., truck, rail, barge, etc.).

        - The following additional items shall be included with the submittal for Stability Classification SC for shipping pieces with shipping length greater than 135 feet:

        - Temporary support locations.

        - Stability calculations demonstrating adequate and stable primary member configuration for handling and shipping to project site, accounting for but not limited to: wind, travel speed (including the values used in calculations for the transport vehicle), and the superelevation of the roadway.

        - Approved mix design for beams/slabs if strength required for handling and shipping exceeds final design strength required by the Contract. In this case, the handling and shipping strength shall be identified on the working drawings. Additional test cylinders shall be planned and produced in accordance with Section 405 of the Specifications.

      - Erection Diagrams, Notes, and Documentation - The erection diagrams, notes, and documentation shall include the following:

        - Erection Sequence – For all stability classes, the Design-Builder shall provide an erection sequence for all primary members (including any attached secondary members).

          - The erection sequence shall be shown on a plan view of the bridge for each erection stage, highlighting: the structural components to be erected and their weights, centers of gravity, and splice locations; lifting crane locations for primary member picks that are necessary during the particular stage; and crane capacity charts. Member Reference Marks shall be the same as used on working drawings.

          - The illustrative plan views described above shall be provided in sufficient detail.  The illustrative plan included with the erection sequence shall be developed with CADD for Class SB and SC structures. In lieu of CADD drawings, scaled drawings or photocopies of the erection plans from the contract plans may be used with the Engineer’s approval. For Class SA structures, the Design-Builder may submit a request to the Design Manager and Engineer to accept a hand sketch or no.

          - A written narrative of the procedure to be followed by the Erector shall be submitted. The narrative shall outline items such as structural components to be erected, and the use and sequence of removal for temporary bracing, anchorage, restraints, blocking, bearing installation, etc.

        - Potential obstructions or restrictions for crane operations – For all stability classes, provide potential obstructions or restrictions to crane operations (e.g., existing structures, utilities, nearby airport operations, etc.).

        - Crane locations, capacity charts, related site conditions – For all stability classes, provide location of each crane to be used for each primary member pick, showing the crane type, crane pick radius, crane support methods (e.g., mats, work trestles, etc.), and the means of attachments to the primary members being lifted or supported. This shall include Crane Capacity Charts or tables that demonstrate the adequacy of each crane configuration, boom length, counterweight configuration, outrigger configuration, and pick weight required. Where additional crane capacity is required by another entity (e.g., Norfolk Southern, CSXT, WMATA, etc.), submittal shall factor the pick weight required appropriately.

        - Rigging detail, weight, capacity, arrangement – For Stability Classes SB and SC, provide details, weight, capacity, and arrangement of all rigging (e.g., beam clamps, lifting lugs, etc.) and all lifting devices (e.g., spreader and lifting beams) required for lifting primary members.

        - Lifting weight of primary member picks – For all Stability Classes, determine all rigging and pre-attached elements (e.g., cross-frames or splice plates); provide lifting weight of primary members, including all rigging and pre-attached elements.

        - Temporary lateral bracing – For Stability Classes SB when skew exceeds 45 deg. and SC, the Erection Engineer shall determine the size, spacing, and location of any temporary lateral bracing necessary to supplement permanent cross-frames for their proposed erection sequence.

        - Temporary devices bolted to permanent members (steel girders and trusses) – For Stability Classes SB and SC, provide details of any temporary rigging or lifting devices to be bolted to permanent members. Welding to any permanent member will not be permitted for any temporary method of attachment.

        - Cross-frame/diaphragm connections (steel girders and trusses) – For Stability Classes SB and SC, provide the number and location of cross-frame or diaphragm connections which shall be made to maintain safety and stability before advancing to the next erection sequence. Include bolting requirements for bolted field splice assembly and cross-frame or diaphragm connections at each stage of construction when the minimums needed exceed the minimum required by Section 407.06 of the Specifications.

        - Certification documents/catalog cuts for pre-engineered devices/equipment – For Stability Class SC, provide Manufacturer’s certification documents or catalog cuts for pre-engineered devices or equipment when these items are used during erection of primary members. These items shall be subject to review by the Design Manager.

        - Proposed removal of a field splice – where the Design-Builder requests the removal of a splice, the Erection Engineer shall provide calculations demonstrating that the modified primary member is structurally adequate and stable for the proposed conditions.

        - Blocking details for bearings – For Stability Class SC, provide blocking details for bridge bearings and necessary girder supports before and after the sole plates are welded to the girders.

        - Temporary tie-down/restraint device details for bearings – For Stability Class SC, provide details for temporary tie-down or restraint devices for bearings which restrict movement in the same direction as final bearing configuration due to applied loads such as wind, thermal, or construction. Load shall be transmitted to the bearings in accordance with Section 408.03(a)-11 of the Specifications.

        - Loading Restrictions – For Stability Class SC, provide any restrictions for wind, construction, dead, and live loading.  Include any other applicable loading restrictions (e.g., maximum wind speed at the time of lift when lower than indicated herein).

        - Temporary Support Structure Details – Provide details of temporary support structures as described herein. If the temporary support is pre-fabricated (e.g., selected from a supplier’s catalog), the type and capacity shall be defined in the Erection Plans. Lateral capacity and vertical capacity requirements shall be considered, as appropriate. If the temporary support is to be constructed by the Design-Builder on site, a complete design with full details, including member sizes, connections, and bracing elements shall be provided. In either case, details related to how the primary members will bear on the temporary support, including elevations at the top of the falsework, shall be included.

Temporary support structure details shall also include:

          - Foundation requirements for temporary support structures: For Stability Class SC, provide foundation requirements for temporary support structures including design of foundations and soil bearing capacities.

          - Strongbacks: Details and placement of strongback for shipping and timing of removal from primary member.

          - Hold cranes: Approximate location of hold cranes used to provide temporary support to the assembly shall be indicated along with the associated crane loads. The crane type, capacity, boom lengths, pick radius, and means of attachment to the primary members shall be indicated.

          - Falsework: Location of falsework used to provide temporary support to the assembly shall include working drawings in accordance with VDOT Road and Bridge Specifications 105.10(c)-2.

5.	Temporary tie-downs: Location and details for temporary tie-downs that are required to facilitate the erection, as well as the associated tie-down loads shall be indicated. The details shall include the tie-down, primary member attachment devices, and anchoring devices.

6.	Primary member restraints: The details shall indicate appropriate restraint of Primary members from twisting and rollover at supports. Primary members shall be restrained from twist and rollover at supports unless the need for such restraint is demonstrated to be unnecessary by appropriate analysis in the Erection Engineering Calculations.

7.	Release or removal of temporary support structures: The details shall indicate when, and under what conditions, any temporary support structures may be released or removed in the erection sequence, or if they may be left in place while subsequent erection proceeds.

        - Jacking Device Details – The Design-Builder shall develop a plan and supporting calculations for jacking, blocking, and supporting beams. Unless approved by the Engineer in writing, all jacks and temporary support systems shall be designed to support traffic loadings, dead load, temporary construction loads, and all other anticipated loading during work requiring the jacking and blocking of beams. The design shall be in accordance with the same edition of AASHTO LRFD Bridge Design Specifications and VDOT Modifications as used for design, unless noted otherwise.  The plans and calculations shall be signed and sealed by a Professional Engineer holding a valid license to practice engineering in the Commonwealth of Virginia.

For Stability Class SC, jacking and blocking details required to complete the erection shall be provided to the Design Manager for review.  Their location, type, size, and capacity shall be indicated, along with their intended use, sequence of engagement, load level, jack pressure table, and any other key operational parameters.

      - Erection Engineering Calculations – Perform all calculations required to erect the structure.

        - Erection Engineering Calculations shall be signed and sealed by the Erection Engineer.

        - The following supporting calculations for each Structural Stability Class shall be submitted for review:

          - For Stability Class SA with steel girders, Class SB with steel girders, and for all Class SC: where the concrete deck placement sequence varies from the plans, calculations shall demonstrate that local flange buckling, lateral torsional buckling, global buckling, uplift, and camber have been verified to meet the appropriate superstructure material requirements.

          - For all Stability Classes, a detailed lifting analysis for primary members shall be performed under the following conditions:

            - For prestressed concrete members:

              - If primary structural members are to be shipped or placed on dunnage with support points other than indicated in the Plans or if the Plans do not indicate appropriate support points, refer to Section 405.05-(h) of the Specifications.

              - Lifting and support points for all primary members shall be as shown on the plans.  If plans do not indicate lifting and support points, or the primary members are to be lifted or supported at points other than indicated in the Plans, the Design-Builder shall lift and support individual primary members at locations in accordance with Section 405.05-(h) of the Specifications.  The Design-Builder shall be responsible for the design and safety of the lifting device used.

            - For structural steel members:

              - If primary structural members are to be transported or placed on dunnage with support points other than indicated in the Plans or if the Plans do not indicate appropriate support points, refer to Section 407.05-(b) of the Specifications.

              - Lifting and support points for all primary members shall be as shown on the plans.  If plans do not indicate lifting and support points or the primary members are to be lifted or supported at points other than indicated in the Plans, the Design-Builder shall support individual primary members in accordance with Section 407.05-(b).  The Design-Builder shall be responsible for the design and safety of the lifting device used.

            - Requests by the Design-Builder to use lifting or support points other than those indicated shall be submitted to the Design Manager for review and shall be accompanied by computations showing that stresses are within the allowable range using an impact factor of 1.50 to the dead load for structures over railroads, and an impact factor of 1.25 to the dead load for all other structures.

For lifting multiple primary members that have been pre-assembled, the Design-Builder shall be responsible for determining appropriate lifting and support points.  The Design-Builder shall include computations using the indicated impact factor and showing that stresses are within the allowable range specified above; the lifting and support point locations shall be indicated in the submittal. All lifting equipment and connection devices shall have sufficient capacity for the actual lifting load plus impact specified above. The factor of safety provided by the manufacturer in the lifting capacity data (i.e., crane capacity charts) shall not be considered as satisfying part of the impact requirement listed herein.

          - The following supporting calculations for Structural Stability Class SC shall be submitted for review:

            - Load capacity and verification of stability for temporary support structures and cranes for each pick and release.

            - Calculations for crane supports (e.g., crane mats, barges, work trestles, etc.) shall be submitted.

            - Structural adequacy and stability of primary members:

              - Prestressed Concrete: Provide compilation of all shipping and erection loads and associated deflections. Substantiate structural adequacy and stability of primary members for each step of bridge assembly in accordance with the current Precast Concrete Institute (PCI) Recommended Practice for Lateral Stability of Precast, Prestressed Concrete Bridge Girders.

                - Factor of Safety against cracking >1.0

                - Factor of Safety against failure > 1.5

If modification to concrete mix is proposed (e.g., for strength, etc.), include the revised concrete mix design data for review.

              - Structural Steel: Substantiate structural adequacy and stability of primary members for each step of bridge assembly for the means and methods used. Provide calculations to demonstrate the primary member does not experience the following:

                - Loads greater than capacity prior to completion of bridge assembly

                - Local flange buckling

                - Lateral torsional buckling

                - Global buckling

                - Uplift

            - Wind loads for erection and lifting on site

            - Wind Case 1 – active work space: wind speed = 20 MPH or equivalent pressure for the maximum safe wind speed under which the cranes are permitted to operate, whichever is greater. Refer to the AASHTO Guide Specifications for Wind Loads on Bridges during Construction.

            - Wind Case 2 – inactive work space: equivalent pressure for the wind speed determined by the 3-second gust wind velocity Figure 4.1.2-1 and may be modified using wind speed reduction factor during construction as specified in Article 4.1.2 of the AASHTO Guide Specifications for Wind Loads on Bridges during Construction.

            - Wind Case 3 – uncured (partial or total) deck pour where the concrete deck placement sequence varies from the plans, in place: refer to the AASHTO LRFD Bridge Design Specification, Section 4.6.2.7.

            - The wind speed shall be increased where records, experience, or site-specific wind studies indicate that wind speeds higher than those in Figure 4.1.2-1 of the AASHTO Guide Specifications for Wind Loads on Bridges during Construction.

            - If drop-in girders are used, calculations for temperature effects for fit-up and stresses due to any required jacking forces shall be provided. Include details for jacking and applied load tables.

            - Calculations verifying adequate capacity of Design-Builder-fabricated rigging such as lift beams, welded lugs, spreader beams, beam clamps, etc. shall be submitted.

            - Calculations verifying adequate structural capacity of any partially-bolted main connections after release of temporary support system shall be submitted.

  - Pre-Erection Meeting: For structures in Stability Class SC, the Design-Builder shall hold a Pre-Erection Meeting for coordination between the Design Manager, Erection Engineer, Erection Supervisor and all other necessary parties involved in the design, inspection, shipping, fabrication, and erection of the structural members. The meeting shall take place after the completion of review of submittals and at least 14 days prior to erection. This meeting shall review, at a minimum, the following:

    - Safety Procedures

    - Handling and Shipping Plan

    - Erection Diagrams, Notes, and Documentation

  - Summary of the meeting and submittal requirements

| TABLE IV-1 CLASS SA |  |
| --- | --- |
| ITEMS | REFERENCE |
| ERECTION PLANS AND PROCEDURES |  |
| Erection Diagrams, Notes, and Documentation | IV.1.B.(2) |
| Erection Sequence | IV.1.B (2).(a) |
| Potential obstructions or restrictions for crane operations | IV.1.B (2).(b) |
| Crane locations, capacity charts, related site conditions | IV.1.B.(2).(c) |
| Erection Engineering Calculations | IV.1.B.(3) |
| Structural adequacy & stability (Steel only) | IV.1.B.(3).(b).i |
| Detailed lifting analysis | IV.1.B.(3).(b).ii |

| TABLE IV-2 CLASS SB |  |
| --- | --- |
| ITEMS | REFERENCE |
| ERECTION PLANS AND PROCEDURES |  |
| Handling and Shipping Plan | IV.1.B.(1) |
| Shipping length & weight | IV.1.B.(1).(a) |
| Truck/rail/barge & load configuration sketches | IV.1.B.(1).(b) |
| Tie-down configuration & tightening process | IV.1.B.(1).(c) |
| Applicable permits (anticipated) & hauling routes | IV.1.B.(1).(d) |
| Method of shipping | IV.1.B.(1).(e) |
| Erection Diagrams, Notes, and Documentation | IV.1.B.(2) |
| Erection sequence | IV.1.B (2).(a) |
| Potential obstructions or restrictions for crane operations | IV.1.B (2).(b) |
| Crane locations, capacity charts, related site conditions, etc. | IV.1.B.(2).(c) |
| Rigging detail, weight, capacity, arrangement | IV.1.B.(2).(d) |
| Lifting weight primary member picks | IV.1.B.(2).(e) |
| Temporary lateral bracing (skew > 45 degrees only) | IV.1.B.(2).(f) |
| Temporary devices bolted to permanent members (steel only) | IV.1.B.(2).(g) |
| Cross-frame/diaphragm connections (steel only) | IV.1.B.(2).(h) |
| Erection Engineering Calculations | IV.1.B.(3) |
| Structural adequacy & stability (Steel only) | IV.1.B.(3).(b).i |
| Detailed lifting analysis | IV.1.B.(3).(b).ii |

| TABLE IV-3 CLASS SC |  |
| --- | --- |
| ITEMS | REFERENCE |
| MEETINGS |  |
| Pre-Erection Meeting | IV.1 |
| ERECTION PLANS AND PROCEDURES |  |
| Handling and Shipping Plan | IV.1.B.(1) |
| Shipping length and weight | IV.1.B.(1).(a) |
| Truck/rail/barge and load configuration sketches | IV.1.B.(1).(b) |
| Tie-down configuration and tightening process | IV.1.B.(1).(c) |
| Applicable permits (anticipated) and hauling routes | IV.1.B.(1).(d) |
| Method of shipping | IV.1.B.(1).(e) |
| Temporary support locations | IV.1.B.(1).(f).i |
| Mix designs – beams/slabs | IV.1.B.(1).(f).iii |
| Erection Diagrams, Notes, and Documentation | IV.1.B.(2) |
| Erection sequence and schedule | IV.1.B (2).(a) |
| Potential obstructions or restrictions for crane operations | IV.1.B (2).(b) |
| Crane locations, capacity charts, related site conditions, etc. | IV.1.B.(2).(c) |
| Rigging detail, weight, capacity, arrangement | IV.1.B.(2).(d) |
| Lifting weight primary member picks | IV.1.B.(2).(e) |
| Temporary lateral bracing (skew > 45 degrees only) | IV.1.B.(2).(f) |
| Temporary devices bolted to permanent members (steel only) | IV.1.B.(2).(g) |
| Cross-frame/diaphragm connections (steel only) | IV.1.B.(2).(h) |
| Cert. documents/catalog cuts for pre-engineered devices/equipment | IV.1.B.(2).(i) |
| Requests to remove splice, including calculations demonstrating | IV.1.B.(2).(j) |
| adequacy |  |
| Blocking details for bearings | IV.1.B.(2).(k) |
| Temporary tie-down / restraint device details for bearings | IV.1.B.(2).(l) |
| Loading restrictions | IV.1.B.(2).(m) |
| Temporary support structure details | IV.1.B.(2).(n) |
| Foundation requirements for temporary support structures | IV.1.B.(2).(n).i |
| Strongback details Hold crane locations Falsework locations Tie-downs and primary member restraints Release or removal of temporary support structures Jacking device details | IV.1.B.(2).(n).ii IV.1.B.(2).(n).iii IV.1.B.(2).(n).iv IV.1.B.(2).(n).v IV.1.B.(2).(n).vi IV.1.B.(2).(o) |
| Erection Engineering Calculations | IV.1.B.(3) |
| Structural adequacy & stability (All primary members) | IV.1.B.(3).(b).i |
| Detailed lifting analysis | IV.1.B.(3).(b).ii |
| Shipping stability calculations | IV.1.B.(1).(f).ii |
| Load capacity and stability of temporary structures | IV.1.B.(3).(b).iii.a) |
| Calculations for crane supports | IV.1.B.(3).(b).iii.b) |
| Structural adequacy and stability (step by step erection) Wind loads for erection and lifting on site | IV.1.B.(3).(b).iii.c) IV.1.B.(3).(b).iii.d) |
| Temperature effects for fit-up (for drop-in girders) | IV.1.B.(3).(b).iii.e) |
| Adequacy of Design-Builder-fabricated rigging | IV.1.B.(3).(b).iii.f) |
| Structural capacity of partially bolted primary members after release of temporary support system | IV.1.B.(3).(b).iii.g) |

- SUBMISSION PROCEDURES

  - The Design-Builder shall submit the Erection Plans and Procedures and all required calculations for the primary members.  The transportation details, e.g., tie-down type, locations and details, and any modifications to the lifting or support locations shall be coordinated between the Fabricator, Erector, and Shipping Provider for incorporation into the working drawings to the greatest extent possible.

  - Erection Plans and Procedures, including subsequent revisions, will be reviewed and returned to the Design-Builder in accordance with Contract requirements.

    - All submissions required herein, and any subsequent revisions to be made, shall be submitted to the Design Manager and the Department with sufficient time to permit review in accordance with the Contract requirements. The Design-Builder shall consider the time required for the various potential review activities (i.e., resubmissions, etc.) and make submissions accordingly.  Submissions shall be made at least 30 days prior to the start of erection activities, as applicable.  Projects requiring railroad review shall be submitted at least 45 days prior to the start of erection activities, as applicable.

    - Changes to the erection procedures, after the initial review of the Erection Plans and Procedures, may require revisions to portions of the Erection Plans and Procedures or working drawings at the Design Manager’s sole discretion.

    - There shall be no contract time extension due to:

      - Any revision to the Erection Plans and Procedures by the Design-Builder, once initially reviewed by the Department.

      - Revisions required due to Design-Builder’s means and methods, or rejection of the Erection Plans and Procedures submittal resulting from the Design Manager’s initial or subsequent review.

  - The Design Manager’s review period for Erection Engineering Calculations submittals required by Section I.1.B, or as directed by the Design Manager, will conform to Contract requirements. Any and all written review comments provided by the Design Manager shall be addressed to the Design Manager’s and the Department’s satisfaction before starting erection operations.

- ADDITIONAL REQUIREMENTS FOR WORKING DRAWINGS

  - Working drawings shall show complete detail drawings of any modifications to permanent structural components, including temporary support or lifting locations, proposed by the Design-Builder with signed and sealed calculations demonstrating the modifications are both necessary and adequate to accommodate proposed erection sequence loads.

  - Working drawings shall show all penetrations or embedded items required for safe shipping and lifting (including erection). Drilling through the web or flange will not be permitted. Bulb tees or similarly shaped beams shall not be stabilized during shipping using tie-downs placed over the top flange unless approved by the Design Manager. During erection, tie downs over the top flange shall only be used if approved by the Design Manager. The Design Manager will only allow tie downs if computations demonstrate that the flange will not crack or deform under the force of tie downs at service load.