Guidelines: Use when requested by the DEM.

SP522-000190-00

# VIRGINIA DEPARTMENT OF TRANSPORTATION

# Special Provision for

# PROTECTION OF WOOD TURTLE

June 19, 2019

I.	Description

The Wood Turtle, a protected species, may occur in close proximity to this project. The Contractor shall implement the protective measures described herein.

II.	Requirements

Prior to beginning work, the Contractor shall obtain the Virginia Department of Game and Inland Fisheries (VDGIF) Wood Turtle Field Observation Form and Wood Turtle Field Information Sheet, available on VDGIF’s website, and clearly post copies of these documents at the construction site. Additionally, all staff working at the construction site shall attend a short briefing by the Department, lasting approximately 10 minutes, which consists of wood turtle identification, monitoring, and documentation requirements. The Contractor shall coordinate briefings through the District Environmental Manager or designee.

Time-of-Year Restrictions depend on whether project activities take place in streams or uplands. Contractors shall follow the appropriate restrictions, as presented below:

- Instream work: A Time of Year Restriction (TOYR) applies on all instream work from October 1 to March 31 with the exception of dewatering and other work within cofferdams, or as otherwise specified by the water quality permits issued for the project.

The Contractor shall install and remove cofferdams outside of the TOYR.

If wood turtles are found within the instream construction area, the Contractor shall stop work and immediately notify the Engineer. The Contractor shall make the site available and accessible for turtle relocation by the Department. Work shall not resume until the Engineer provides a written notice to proceed.

- Upland work: A TOYR applies on all land-clearing or upland soil-disturbing activities within 300 feet of the water from April 1 to September 30. If the Contractor requires access to these areas during the TOYR, the Contractor shall request approval from the Engineer to access the restricted area. If approved by the Engineer, the Contractor shall install silt fence to create a delineated work area. An initial wood turtle relocation by the Department will be required prior to work within the delineated work area.

Each day, following initial relocation efforts, the Contractor shall visually inspect the delineated work area for wood turtles prior to beginning work. If turtles are found within the delineated work area, the Contractor shall immediately stop work within the delineated work area and notify the Engineer to initiate turtle relocation by the Department. Work shall not resume within the delineated work area until the Engineer provides a written notice to proceed.

- Measurement and Payment

No separate payment will be made for compliance with the requirements herein.