Guidelines: Use when requested by the DEM. Fill in the highlighted section.

SP522-000280-00

VIRGINIA DEPARTMENT OF TRANSPORTATION

Special Provision for

pROTECTION OF THE BIG SANDY CRAYFISH

June 19, 2019

I.	Description

Stream Name is known to provide habitat for the Big Sandy Crayfish, a state and federally protected species. The Contractor shall take protective measures as described herein.

II.	Requirements

A Time of Year Restriction (TOYR) applies on all instream work from July 1 through October 31 with the exception of dewatering and other work within cofferdams, or as otherwise specified by the water quality permits issued for the project.

The Contractor shall install and remove cofferdams outside of the TOYR. The Contractor shall notify the Engineer at least 30 days before cofferdam placement, or a different notification timeframe as approved by the Engineer, and shall allow the Department’s biologists to perform Big Sandy Crayfish relocation activities within all cofferdams. The Contractor shall not begin work within cofferdams until the crayfish relocation activities are completed, and the Engineer provides a written notice to proceed.

If the cofferdam overtops due to excessive stream flow after initial relocation efforts are completed, additional crayfish relocation will be required before subsequent dewatering activities. The Department will conduct additional crayfish relocation activities within 3 working days after receiving written notification of the overtopping.

- Measurement and Payment

No separate payment will be made for compliance with the requirements herein.