Guidelines: Use only on Bristol District schedule work projects advertised between October 1, 2022 and December 31, 2023.

SQ108-000300-00

VIRGINIA DEPARTMENT OF TRANSPORTATION

SPECIAL PROVISION FOR

LIMITATION OF OPERATIONS

(BRISTOL DISTRICT)

September 22, 2022

SECTION 108.02 - LIMITATION OF OPERATIONS is amended as follows:

Section 108.02(a) - General of the Specifications is amended to include the following:

All work areas (and the limits thereof) and lane closures shall be in accordance with the 2011 Virginia Work Area Protection Manual and latest revisions and shall be approved by the Engineer.

No lane closure signing or other traffic disruptive work is to be initiated prior to those times specified. All signs, equipment, and materials shall be removed prior to the ending closure time indicated. No lane closures are to be permitted without the written permission of the Engineer.

When the Contractor works at night, they shall provide sufficient lighting of the work sites(s) to enable the satisfactory completion of work. Lighting shall arrange so as not to interfere with or impede traffic approaching the work site from either direction. Lighting arrangement at the work site(s) shall provide a minimum of 50 foot candles of light for an area of approximately 15 feet by 15 feet with minimum of 5 foot candles in the corners of the area. Lighting shall be a minimum of two fixtures with backup fixtures and power source readily available.

The Contractor shall determine the applicable lane closure and shoulder closure hours from the following lane closure tables for the specified routes listed in the Contract; however, the Engineer may change any or all of the work hours detailed in the following lane closure tables.

Section 108.02(b) - Holidays is amended to include “Special Events” and the following:

- Bristol NASCAR Races: Interstate 81 from the Tennessee state line to the Pulaski County line, Interstate 77 from the Carroll County line to the West Virginia state line, and Interstate 381 from 12:00 p.m. on the Wednesday before the scheduled race to 6:00 a.m. on the Tuesday following the race. Race schedules can be found at  www.nascar.com.

- Any other special event that may increase traffic on a specific route as directed by the Engineer