GUIDELINES —Where **Define project segment or portion of work to be completed**, “$Provide amount” and **Month dd, yyyy** is shown, the work location, justified dollar amount and date documented in the project file must be filled in.  This substantial completion is defined as “returning beneficial use.  This provision should be used when a specific portion of a project must be completed on or before a given date (i.e., phased construction).

cn108-000412-02	INTERIM COMPLETION INCENTIVE/DISINCENTIVE

The following terms are defined:

●	Interim Completion is defined as completing all work as detailed herein. The following work must be completed for Interim Completion: **Define project segment or portion of work to be completed**

●	Interim Completion Date is the date on or before which all work required for Interim Completion must be completed such that the Contractor receives an incentive. Otherwise, a disincentive is assessed each day thereafter the Interim Completion requirements are not met. This date will not change except for an extension of the Contract time limit for a Compensable Delay as defined by Section 109.05(e) of the Specifications.

The Interim Completion Date is ** Month dd, yyyy **. The Department will pay an incentive of $Provide amount for each Calendar Day before the Interim Completion Date as adjusted by the Engineer for Compensable Delay that the Interim Completion requirements are met. The incentive is capped at $Provide Amount.

If the Interim Completion requirements are not met on or before  the Interim Completion Date as adjusted by the Engineer for Compensable Delay, the Department will assess a disincentive in the amount of $Provide amount for each Calendar Day after the Interim Completion Date as adjusted by the Engineer for Compensable Delay that the Contractor does not achieve Interim Completion as defined herein. The disincentive is capped at $Provide Amount.

The disincentive will be assessed, not as a penalty, but as agreed compensation for damages resulting from the Contractor's delay. The disincentive amount is calculated based on Department related traffic control and maintenance costs, detour costs, or daily road user costs, as applicable.

The Contractor waives any defense as to the validity of any disincentives stated in the Contract, the Specifications, or this Special Provision, and assessed by the Department against the Contractor on the grounds that such disincentives are void as penalties or are not reasonably related to actual damages.

9-10-19 (SPCN)