GUIDELINES — Plant mix schedule projects only. {2007-c515c00}

cn515-000100-02	DISINCENTIVE FOR PLANING IN MULTIPLE LANES

The Special Provision for COLD PLANING (MILLING) ASPHALT CONCRETE OPERATIONS “SP515-000100-00” dated July 12, 2016 is amended as follows:

Section III.A.1.  Regular planing and performance planing in multiple lanes is amended to replace the first bulleted subparagraph of the fourth paragraph with the following:

●	The Contractor will be limited in the case of regular pavement planing, whether in a single lane or multiple lane operation, to only that amount of pavement that can be paved back within 24 hours of completion of planing that roadway or portion of roadway. Single-lift operations must be restored to final elevation to satisfy this requirement. If the Contractor elects not to pave back the planed travel lanes within 24 hours from the end of the regular planing operation, or is prevented from doing so by predictable weather, the Department will assess a disincentive in the amount of $5,000 for each calendar day the planed travel lane surface is not paved back, including Sundays and Holidays.

Section III.A.1. Regular planing and performance planing in multiple lanes is amended to replace the first bulleted subparagraph of the fifth paragraph with the following:

●	Performance pavement planing may be performed in multiple lanes across the entire widths of the lanes up 4 miles of travel lane unless otherwise stated in the Contract.  Performance planed travel lane surfaces must be paved back within 96 hours from the end of the performance planing operation. Single-lift operations must be restored to final elevation to satisfy this requirement. If the Contractor elects not to pave back the planed travel lanes within 96 hours from the end of the performance planing operation, or is prevented from doing so by predictable weather, the Department will assess a disincentive in the amount of $5,000 for each calendar day the planed travel lane surface is not paved back, including Sundays and Holidays.

11-23-16 (SPCN)